## Sheet1
Bug Id | Title | Priority | Severity | Enviorment | Description | Bug Steps | Expected Behavior | Actual Behavior | Additional Notes | Test Executed By | Screenshots
Sub_01 | Pricing Glitch. | Medium. | Major. | IOS/iphone. | When navigating between the Commercial and Enterprise pricing plans in the Pricing section of the navigation bar, a glitch occurs where the Enterprise slide briefly moves downward for a few seconds before returning to its correct position. This issue affects the user experience and may lead to confusion or frustration among users. | 1-Navigate to the Pricing section of the navigation bar. 2-Select the Commercial pricing plan. 3-Swipe or click to navigate to the Enterprise pricing plan. 4-Observe the Enterprise slide momentarily shifting downward before stabilizing. | When switching between the Commercial and Enterprise pricing plans, the Enterprise slide should smoothly transition without any sudden movements or shifts in position. | Upon navigating from the Commercial to the Enterprise pricing plan, the Enterprise slide briefly moves downward for a few seconds before returning to its correct position. | This glitch impacts the overall user experience, especially for users comparing pricing plans or considering upgrading to the Enterprise tier. It is recommended to investigate and address this issue promptly to ensure a seamless navigation experience for users across all pricing plans. | Vishesh Dobhal | https://drive.google.com/file/d/1QDxbcXV1MPAV0tRBtiahzTfkDJsrLMg_/view?usp=sharing
Sub_02 | Comment Box Content Overlap Issue. | Medium. | Major. | IOS/iphone. | When navigating between slides in the comment box feature of the Ratio interface, there is an issue where content from the previous slide briefly appears on the subsequent slide. This overlapping of content disrupts the user experience and may lead to confusion or misinterpretation of comments. | 1-Access the comment box feature within the Ratio interface. 2-Navigate through the slides by swiping or clicking to move to the next slide. 3-Observe that as you transition to the next slide, content from the previous slide briefly appears before the new slide content fully loads. | When moving to the next slide in the comment box, the content of the previous slide should be completely cleared, and only the content relevant to the current slide should be displayed without any overlap or interference. | Upon transitioning to the next slide, there is a brief moment where content from the previous slide is visible before it disappears, causing an overlap with the content of the current slide. | This content overlap issue undermines the usability of the comment box feature within the Ratio interface. It is crucial to address this issue promptly to ensure a seamless and uninterrupted viewing experience for users navigating through the slides and reading comments. Investigating the root cause of this problem and implementing a fix will enhance the overall user experience and improve engagement with the comment feature. | Vishesh Dobhal. | https://drive.google.com/file/d/1KG5DRVFihdko2ZinMogJe1vrOWjWgEPu/view?usp=sharing
Sub_03 | Incomplete Display of Comment Box Content. | Medium. | Minor. | IOS/iphone. | In the Ratio comment box feature, users are experiencing an issue where the entire content of comments is not displayed within the designated area. This leads to users not being able to view the entirety of comments, causing frustration and potentially missing important feedback. | 1-Access the comment box feature within the Ratio interface. 2-Navigate to a slide where comments are present. 3-Observe that some comments are truncated or cut off, not displaying the full content. 4-Attempt to scroll or interact with the comment box to view the complete comments. | All comments within the comment box should be fully displayed, allowing users to read the entirety of each comment without any truncation or cut-off. | Some comments within the comment box are not fully displayed, with the content being truncated or cut off, preventing users from reading the complete comments. | This issue impacts the usability of the comment box feature within the Ratio interface, as users may miss valuable feedback or discussions due to incomplete display of comments. It is essential to ensure that all comments are fully visible within the designated area to provide users with a seamless and effective commenting experience. Investigating the cause of this issue and implementing a solution to display complete comments will enhance user satisfaction and engagement with the comment feature. | Vishesh Dobhal. | https://drive.google.com/file/d/1Q3kycvjzHfay4lrVvy526Rofb2uyBlRk/view?usp=sharing
Sub_04 | Logo Image and Text Overlap Issue in Home Section. | Medium. | Minor. | IOS/Iphone. | In the Home section of the navigation bar, there is a problem with the layout where the logo images are too close to the accompanying text in four out of six boxes. This results in an overlap between the logo image and the text, affecting the readability and visual presentation of the content. | 1-Navigate to the Home section of the navigation bar. 2-Observe the layout of the six boxes containing logo images and text. 3-Notice that in four of the boxes, the logo images are positioned too closely to the text, causing overlap. | In the Home section, the layout should ensure an appropriate spacing between the logo images and the accompanying text, preventing any overlap and maintaining a visually appealing design. | The logo images in four of the boxes within the Home section are positioned too close to the text, resulting in overlap and impacting the overall aesthetics and readability of the content. | This overlap issue in the Home section affects the user experience by making it difficult for users to distinguish between the logo images and the accompanying text. It is important to review and adjust the layout to ensure proper spacing between elements, thereby improving readability and visual consistency across all sections of the navigation bar. Addressing this issue promptly will enhance the overall usability and aesthetics of the interface. | Vishesh Dobhal. | https://drive.google.com/file/d/1HBOyqiwR5zMyEwrJ6CvD5ncpZtOtbRCX/view?usp=sharing
Sub_05 | Incorrect Label in About Section. | Low. | Minor. | IOS/Iphone. | In the navigation bar, specifically within the About section, the label "LOGO" is displayed instead of the actual logo image. This inconsistency between the label and expected content may confuse users and detract from the overall user experience. | 1-Navigate to the About section of the navigation bar. 2-Observe the label displayed in place of the logo image. | In the About section of the navigation bar, the actual logo image should be displayed instead of a text label. | The label "LOGO" is displayed in the About section instead of the expected logo image. | While this issue is relatively minor, it may cause confusion for users expecting to see the logo image in the About section. To ensure consistency and clarity in the navigation bar, it is recommended to correct this labeling error and display the appropriate logo image as intended. This adjustment will enhance the visual appeal and usability of the navigation bar. | Vishesh Dobhal. | https://drive.google.com/file/d/12biR97IBPWViKI3z2iXdMfV1jOj2ybmG/view?usp=sharing
sub_06 | Lack of Message Delivery Confirmation in Contact Us Feature | Medium. | Major. | IOS/Iphone | In the About section, specifically within the Contact button, there is a Contact Us feature where users can send messages. However, after sending a message, there is no confirmation displayed to indicate whether the message was successfully delivered or not. This lack of feedback leaves users uncertain about the status of their messages and may lead to confusion or frustration. | 1-Navigate to the About section. 2-Click on the Contact button to access the Contact Us feature. 3-Fill out the message form and submit the message. 4-Observe that there is no confirmation message or indication of whether the message was successfully delivered. | After sending a message through the Contact Us feature, users should receive a confirmation message or visual indication confirming that their message was successfully delivered. | Upon sending a message through the Contact Us feature, there is no confirmation displayed to indicate whether the message was successfully delivered or not. | The absence of message delivery confirmation in the Contact Us feature hinders the user experience by leaving users uncertain about the status of their messages. Implementing a confirmation message or visual indication upon successful message delivery will provide users with reassurance and improve their overall satisfaction with the contact feature. It is recommended to address this issue promptly to enhance user engagement and communication through the Contact Us feature. | Vishesh Dobhal. | https://drive.google.com/file/d/1YLpS5bZ5lrbbedpOmtPyD9RIlNbiQyJT/view?usp=sharing
sub_07 | Misalignment of Buttons in About Section. | Low. | Minor. | IOS/Iphone. | In the About section, there is a misalignment issue with the four buttons present. The buttons are not arranged in an accurate line, which affects the overall visual consistency and may cause discomfort to users with an eye for detail. | 1-Navigate to the About section of the application. 2-Observe the arrangement of the four buttons. 3-Notice that the buttons are not aligned properly in a straight line. | In the About section, the four buttons should be arranged in a neat and accurate line, ensuring visual harmony and consistency. | Upon inspection, it is evident that the buttons in the About section are misaligned, deviating from the expected straight line arrangement. | While this issue is relatively minor and does not impact functionality, it does affect the visual aesthetics of the About section. Ensuring proper alignment of the buttons will contribute to a more polished and professional appearance of the interface, enhancing the overall user experience. It is recommended to address this misalignment to maintain visual consistency throughout the application. | Vishesh Dobhal. | https://drive.google.com/file/d/196pQb_Zl4drXel2rTrenqaUHdzw5W0Hj/view?usp=sharing
Sub_08 | Social Media Buttons in Footer "Follow Us" Section. | High. | Major. | IOS/Iphone. | The "Follow us" section in the footer of the website contains buttons for Facebook, Instagram, LinkedIn, and Twitter, which do not function as expected. When users attempt to click on these buttons, they do not navigate to the corresponding social media profiles. This issue significantly impacts user engagement and usability, as it prevents users from easily accessing and following the website's social media presence. | 1-Navigate to the footer section of the website. 2-Locate the "Follow us" option. 3-Attempt to click on the buttons for Facebook, Instagram, LinkedIn, and Twitter. 4-Observe that clicking on these buttons does not lead to the respective social media profiles. 5-Note any lack of visual or auditory feedback indicating that the buttons are clickable. 6-Verify that the links attached to these buttons are not functioning. | When navigating to the footer section of the website, locate the "Follow us" option. The buttons for Facebook, Instagram, LinkedIn, and Twitter should be clickable. Upon clicking on each button, users should be redirected to the respective social media profiles associated with the website. | Upon navigating to the footer section of the website and locating the "Follow us" option, The buttons for Facebook, Instagram, LinkedIn, and Twitter are present but non-functional. Clicking on these buttons does not lead to the respective social media profiles; no redirection occurs. | It's important to verify whether the issue is consistent across all pages of the website or if it's limited to specific pages. Check if there are any recent changes or updates to the website that might have caused the buttons to malfunction. Review the website's codebase to ensure that there are no coding errors or conflicts affecting the functionality of the buttons. | Vishesh Dobhal | https://drive.google.com/file/d/1Qs_SiHH6zpATkxA5YrU6bQmeYgL_hDnq/view?usp=sharing